## GanttChart
Capstone
FCE
| Project Start Date | 2022-01-26 |  |  |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19
| Project Lead | [7 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30
 | time axis 2022-01-24 to 2022-06-05
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2022-01-24 to 2022-06-05
1 | Identify Group
0.1 | Creation of Group | Team/Beck |  | 2022-01-26 | 2022-01-27 | 2 | 100% | 2
0.1 | First Sponsor Meeting | Team/Sponsor |  | 2022-01-28 | 2022-01-28 | 1 | 100% | 1
0.1 | Develop Sketch/Project Plan | Team |  | 2022-02-01 | 2022-02-08 | 8 | 100% | 6
0.1 | Present Project Plan | Team |  | 2022-02-09 | 2022-02-09 | 1 | 100% | 1
0.1 | Create Project Presenation | Team |  | 2021-09-21 | 2021-09-30 | 5 | 100% | 8
1 | Develop a complete Data Structure for Transmission
0.1 | Obtain data and python script from sponsor | Magenta team |  | 2022-02-02 | 2022-02-11 | 10 | 100% | 8
0.1 | Summarize and Review the entire data set | Magenta team |  | 2022-02-10 | 2022-02-18 | 9 | 100% | 7
0.1 | Apply data visualization to all data | Magenta team |  | 2022-02-18 | 2022-02-22 | 5 | 100% | 3
0.1 | Sample or generate data for each transmission line and grid | Magenta team |  | 2022-02-22 | 2022-03-07 | 14 | 100% | 10
0.1 | Create test set for entire data | Magenta team |  | 2022-03-29 | 2022-04-11 | 14 | 60% | 10
2.6 | Compare with distribution data | Magenta team |  | 2022-04-11 | 2022-04-17 | 7 | 0% | 5
1 | Develop a complete Data Structure for Distribution
0.1 | Obtain data and python script from sponsor | Magenta Team |  | 2022-02-02 | 2022-02-11 | 10 | 0% | 8
0.1 | Process the available data | Magenta Team |  | 2022-02-10 | 2022-02-18 | 1 | 0% | 7
0.1 | Create visualizations from available data | Magenta Team |  | 2022-02-18 | 2022-02-22 | 5 | 0% | 3
0.1 | Sample data into sets for neighborhood and building study | Magenta Team |  | 2022-02-22 | 2022-03-07 | 14 | 0% | 10
0.1 | Create test set for transmission system creation | Magenta Team |  | 2022-03-29 | 2022-04-11 | 14 | 0% | 10
1 | Create Transmission System
0.1 | Download PSSe | Cyna Team |  | 2022-02-03 | 2022-02-09 | 7 | 100% | 5
0.1 | Complete PSSe Training | Cyna Team |  | 2022-02-05 | 2022-02-16 | 12 | 10% | 8
0.1 | Have a follow-up meeting with sponsors on Training | Cyna Team |  | 2022-02-16 | 2022-02-16 | 1 | 0% | 1
0.1 | Practice with test case on PSSe | Cyna Team |  | 2022-02-16 | 2022-02-22 | 7 | 0% | 5
| Mini Project | Cyna Team |  | 2022-02-23 | 2022-03-07 | 13 | 0% | 9
0.1 | Build substations according to Transmission Data | Cyna Team |  | 2022-03-29 | 2022-04-11 | 14 | 0% | 10
0.1 | Build Load substations | Cyna Team |  | 2022-04-11 | 2022-04-17 | 7 | 0% | 5
0.1 | Build Generation Substations | Cyna Team |  | 2022-04-17 | 2022-04-23 | 7 | 0% | 5
0.1 | Create a synthetic network using Delaunny triangluation | Cyna Team |  | 2022-04-23 | 2022-04-29 | 7 | 0% | 5
0.1 | Connect Substations with the transmission network at multiple voltage levels | Cyna Team |  | 2022-04-29 | 2022-05-05 | 7 | 0% | 5
1 | Create Distribution System
0.1 | Download Windmil Milsoft | Cyna Team |  | 2022-02-03 | 2022-02-09 | 7 | 50% | 5
0.1 | Complete Windmil Milsoft Training | Cyna Team |  | 2022-02-05 | 2022-02-16 | 12 | 10% | 8
0.1 | Have a follow-up meeting with sponsors on Training | Cyna Team |  | 2022-02-16 | 2022-02-16 | 1 | 0% | 1
0.1 | Practice with test case on Windmil Milsoft | Cyna Team |  | 2022-02-16 | 2022-02-22 | 7 | 0% | 5
0.1 | Mini Project | Cyna Team |  | 2022-02-23 | 2022-03-07 | 35 | 0% | 9
0.1 | Plot distribution lines according to data (distribution data) | Cyna Team |  | 2022-03-29 | 2022-04-11 | 11 | 0% | 10
0.1 | Locate and size distribution transformers | Cyna Team |  | 2022-04-11 | 2022-04-17 | 7 | 0% | 5
0.1 | Locate and size different voltage level distribution substations | Cyna Team |  | 2022-04-17 | 2022-04-23 | 7 | 0% | 5
0.1 | Create a synthetic network using Delaunny triangluation | Cyna Team |  | 2022-04-23 | 2022-04-29 | 7 | 0% | 5
1 | Validation of Transmission System
0.1 | Create a testing criteria | Magenta Team |  | 2022-03-29 | 2022-04-12 | 15 | 0% | 11
0.1 | Perform simulation and power flow studies on the synthetic system to generate sythetic system metric | Cyna Team |  | 2022-04-29 | 2022-05-05 | 7 | 0% | 5
0.1 | Synthetic transmission system's metrics' values are compared with the testing critieria | Cyna Team |  | 2022-04-29 | 2022-05-05 | 3 | 0% | 5
0.1 | Perform data analysis on the values | Team |  | 2022-03-29 | 2022-05-05 | 30 | 0% | 28
0.1 | Separate safety and Ethical Analysis on the system | Team |  | 2022-03-29 | 2022-04-04 | 7 | 0% | 5
0.1 | Expert Validation from Sponsors | Team |  | 2022-05-05 | 2022-05-11 | 7 | 0% | 5
1 | Validation of Distribution System
0.1 | Create a testing criteria | Team |  | 2022-03-29 | 2022-04-12 | 15 | 0% | 11
0.1 | compare statistical data to synthetic data | Magenta team |  | 2022-04-29 | 2022-05-05 | 7 | 0% | 5
0.1 | operational validation that simulates use cases | Cyna Team |  | 2022-05-01 | 2022-05-03 | 3 | 0% | 2
0.1 | Perform data analysis on the values | Magenta team |  | 2022-04-29 | 2022-05-08 | 10 | 0% | 6
0.1 | Separate safety and Ethical Analysis on the system | Team |  | 2022-03-29 | 2022-04-04 | 30 | 0% | 5
0.1 | Expert Validation from Sponsors | Team |  | 2022-05-05 | 2022-05-11 | 30 | 0% | 5
1 | Scenario Analysis
0.1 | Collect time series load data | Team |  | 2022-05-11 | 2022-05-17 | 7 | 0% | 5
0.1 | add models to time series data | Team |  | 2022-05-17 | 2022-05-18 | 2 | 0% | 2
0.1 | add distributed energy resources to models | Team |  | 2022-05-18 | 2022-05-19 | 2 | 0% | 2
0.1 | Perform simulations on models for transmission and distribution | Team |  | 2022-05-20 | 2022-05-21 | 2 | 0% | 1
0.1 | Construct a scenario analysis report | Team |  | 2022-05-23 | 2022-05-24 | 2 | 0% | 2
Note on A7: ====== ID#AAAAVMQQ3Bg Vertex42 (2022-02-09 03:37:26) Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: ====== ID#AAAAVMQQ3B0 Vertex42 (2022-02-09 03:37:26) Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: ====== ID#AAAAVMQQ3Bo Vertex42 (2022-02-09 03:37:26) Task Lead Enter the name of the Task Lead in this column.
Note on D7: ====== ID#AAAAVMQQ3B4 Predecessor Tasks (2022-02-09 03:37:26) You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: ====== ID#AAAAVMQQ3Bc Vertex42 (2022-02-09 03:37:26) Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: ====== ID#AAAAVMQQ3Bs End Date (2022-02-09 03:37:26) The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: ====== ID#AAAAVMQQ3Bk Vertex42 (2022-02-09 03:37:26) Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: ====== ID#AAAAVMQQ3Bw Vertex42 (2022-02-09 03:37:26) Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: ====== ID#AAAAVMQQ3B8 Vertex42 (2022-02-09 03:37:26) Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.